## time frame
|  |  |  | S.NO | Requirements
|  |  |  | 1. | Read and write analog values
|  |  |  | 2. | Digital I/O
|  |  |  | 3. | Communications(PWM,UART,I2C;SPI)
|  |  |  | 4. | possibily with another microcontroller
| Time frame | Task | status
| AUGUST | literature/state of art
| SEPTEMBER | concept phase , building basic model
| OCTOBER | development
| NOVEMBER | testing
| DECEMBER | corrections, start documentation
| JANUARY | documentation
checklist/testcases
2 | concept phase |  |  | 1. | Read analog voltages from (0-5V)
2.1 | choosing predominant µ_controllers and peripherals | 5th sept ---- 9th sept |  | 2. | Write analaog voltages(0-10V)
2.2 | understanding the peripheral usage and setting limits | 12.09 ---16.09 |  | 3. | usage of GPIO pins
| UART |  |  | 4. | write to external register/memory using communications
| SPI |  |  | 5. | read the data in external device using communication
| I2C |  |  | 6. | test the thing using another MCU
GPIO
2.3 | USER interface preview
3 | DEVELOPMENT
| 1st µ-controller with analog | 19.09----22.09
| 1st µ-controller with GPIO | 23.09 ---28.09
| 1st µ-controller with Communications | 29.09---05.10
| 2nd µ-controller with Analog | 06.10---12.10
| testing & possible corrections | 13.10---20.10
| continue with 2nd µ-controller | 21.10---20.11
| improvements and corrections | 21.11--2.12
4 | Documentation
| user manual for the user & DEVELOPER | 5.12---15.12
| thesis documentation | 15.12 ---30.01
1. | Literature study
2 | concept phase
2.1 | choosing predominant µ_controllers and peripherals | 5th sept ---- 9th sept
2.2 | understanding the peripheral usage and setting limits | 12.09 ---16.09
UART
SPI
I2C
GPIO
2.3 | USER interface preview
3 | DEVELOPMENT
| 1st µ-controller with analog | 19.09----22.09
| 1st µ-controller with GPIO | 23.09 ---28.09
| 1st µ-controller with Communications | 29.09---05.10
| 2nd µ-controller with Analog | 06.10---12.10
| testing & possible corrections | 13.10---20.10
| continue with 2nd µ-controller | 21.10---20.11
| improvements and corrections | 21.11--2.12
4 | Documentation
| user manual for the user & DEVELOPER | 5.12---15.12
| thesis documentation | 15.12 ---30.01

## idea evaluation criteria
s.no | criteria | idea 1 | idea 2 | idea 3
development
1 | work load for development
licensing
complexity
how big is the software
2 | maintenance
updating the database of controllers
3 | scope
limitations
how far can it be extended
user side
4 | need for additional interface hardware
5 | usage friendly
prior knowledge requirements
easy selection
load on the user(modifications,….)
IDEA 1: creating a skeleton code and taking values from the user interface and generating a final code and save it onto a desktop . compile using (IAR) workbench.
IDEA 2:usage of AUTOSAR.
IDEA 3: using matlab embedded coder.

## Sheet2
| vendor independent |  | Model based |  | vendor specific
| AUTOSAR | CMSIS | TargetLink | Embbeded coder | ATMEL | TI | STMicroelectronics
Platfrom independent | 1 | 1 | 1 | 1 | 0 | 0 | 0
open platform (licensing) | 0 | 1 | 0 | 0 | 1 | 1 | 1
training | 1 | 0.5 | 1 | 1 | 0 | 0 | 0

## chossing u-controller and perip
Most frequently used.
| USER 1 | USER 2 | USER 3 | USER 4 | USER 5 | USER 6 | USER 7 | USER 8 | USER 9
ATMEL | bar: USER 2
ARM controller | bar: USER 1
TI controllers | bar: USER 2
MITSUBUSHI | bar: USER 2
MSP430 | bar: USER 1 to USER 2
ARDUINO | bar: USER 1
top two of the list and their specifications comparision
clock speed
voltages
flash size
SRAM
pin pakage
instruction set
buffer size
ATMEL : SAM7X,SAM4X
ARM: cortex m4
ti controllers:
mitsubishi - Renesas: m16 &m32 series
MSP430X: MSP430F5152
ARUDINO:

## Sheet1
s.no | task list | start date | end date
1. | Literature
2 | concept phase
2.1 | choosing predominant µ_controllers and peripherals | 2016-09-05 | 2016-09-09
2.2 | understanding the peripheral usage and setting limits | 2016-09-12 | 2016-09-15
2.3 | USER interface preview | 2016-09-16 | 2016-09-16
3 | DEVELOPMENT
| 1st µ-controller with analog | 2016-09-19 | 2016-09-22
| 1st µ-controller with GPIO | 2016-09-23 | 2016-09-28
| 1st µ-controller with Communications | 2016-09-29 | 2016-10-05
| 2nd µ-controller with Analog | 2016-10-06 | 2016-10-12
| testing & possible corrections | 2016-10-13 | 2016-10-20
| continue with 2nd µ-controller | 2016-10-21 | 2016-11-20
| improvements and corrections | 2016-11-21 | 2016-12-02
4 | Documentation
| user manual for the user & DEVELOPER | 2016-12-05 | 2016-12-15
| thesis documentation | 2016-12-15 | 2016-01-30